## Read Me
PMO Tracker (SYNTHETIC DEMO DATA, not real company or GMP data)
How to use:
Blue text = inputs you type. Black text = formulas; do not overwrite.
Milestones: edit Status, Baseline, Forecast, Critical Path. Slip and RAG update automatically.
Risks: score Severity, Occurrence, Detection 1-10 (pFMEA style). RPN = S x O x D.
Dashboard: read-only roll-up per project.
RAG rule (same as .claude/skills/pmo-status-report):
Complete = Green. Red = Delayed, or critical path slip > 30 days.
Amber = At Risk, or slip 8-30 days. Otherwise Green.
Risk action threshold: RPN > 100 = Mitigate (assumption; set your own in Dashboard!B12).

## Milestones
Project | Workstream | Milestone | Owner | Baseline Date | Forecast Date | Status | Critical Path (Y/N) | Slip (days) | RAG
TT-MR-Vaccine-SiteB | Process | Process description & PFD frozen | MSAT | 2026-07-15 | 2026-07-20 | Complete | Y
TT-MR-Vaccine-SiteB | Analytical | Analytical method transfer protocol approved | QC | 2026-08-01 | 2026-08-25 | In Progress | Y
TT-MR-Vaccine-SiteB | Equipment | Bioreactor IQ/OQ complete | Engineering | 2026-08-15 | 2026-09-30 | Delayed | Y
TT-MR-Vaccine-SiteB | Quality | Change control CC-2026-118 approved | QA | 2026-07-30 | 2026-07-30 | Complete | N
TT-MR-Vaccine-SiteB | Process | Engineering batch 1 executed | Production | 2026-09-15 | 2026-10-20 | At Risk | Y
TT-MR-Vaccine-SiteB | Regulatory | Post-approval change filing strategy agreed | RA | 2026-09-01 | 2026-09-10 | In Progress | N
TT-MR-Vaccine-SiteB | Process | PPQ protocol approved | QA | 2026-10-15 | 2026-11-15 | Not Started | Y
TT-MR-Vaccine-SiteB | Process | PPQ batches 1-3 executed | Production | 2026-11-30 | 2027-01-10 | Not Started | Y
TT-MR-Vaccine-SiteB | Regulatory | Variation dossier (Module 3) submitted | RA | 2027-01-31 | 2027-03-05 | Not Started | Y
TT-Rabies-CDMO | Analytical | Potency assay transfer report signed | QC | 2026-08-20 | 2026-08-18 | Complete | Y
TT-Rabies-CDMO | Supply | Critical raw material 2nd source qualified | Procurement | 2026-09-30 | 2026-12-15 | Delayed | N
TT-Rabies-CDMO | Process | Scale-down model qualified | MSAT | 2026-09-20 | 2026-09-25 | In Progress | Y

## Risks
Risk ID | Project | Risk | Category | Severity (1-10) | Occurrence (1-10) | Detection (1-10) | RPN | Action | Owner | Mitigation
R-01 | TT-MR-Vaccine-SiteB | Bioreactor IQ/OQ delay pushes engineering batch | Equipment | 8 | 7 | 3 |  |  | Engineering | Vendor FAT punch-list daily call; parallel OQ protocol review
R-02 | TT-MR-Vaccine-SiteB | Analytical method transfer fails acceptance criteria | Analytical | 9 | 4 | 4 |  |  | QC | Pre-transfer comparability run on 3 lots
R-03 | TT-MR-Vaccine-SiteB | Health authority asks for extra stability data | Regulatory | 7 | 5 | 6 |  |  | RA | Pre-submission meeting; start bridging stability now
R-04 | TT-Rabies-CDMO | Single-source raw material supply interruption | Supply | 9 | 5 | 5 |  |  | Procurement | Safety stock 6 months; accelerate 2nd source
R-05 | TT-Rabies-CDMO | Scale-down model not representative | Process | 6 | 3 | 4 |  |  | MSAT | Statistical equivalence (TOST) on key CQAs
R-06 | TT-MR-Vaccine-SiteB | Key MSAT SME attrition | Resource | 5 | 3 | 2 |  |  | PMO | Knowledge-transfer plan; backup SME named

## Dashboard
Project | Red | Amber | Green | Project RAG | Risks to Mitigate | Worst Slip (days)
TT-MR-Vaccine-SiteB
TT-Rabies-CDMO
Settings
RPN action threshold | 100 | Assumption: common pFMEA cut-off; adjust to your site's risk SOP
Built 02-Oct-2026 from labs/tt_milestones.csv